## Hoja1
| Total estimated hours | Total applied hours | Log of average estimation deviation |  | Tasks | Estimated hours | Applied hours | Desviation time
Jorge | 114.35 | 160.55 | -46.2 | Aitor | Qa Plan | 2 | 2 | 0
Jaume | 152.5 | 180.9 | -28.4 |  | Audio Bible | 2 | 3 | -1
Sergio | 58.5 | 106 | -47.5 |  | Sorting/listening audios | 2 | 3 | -1
Aurelio | 145.75 | 185.05 | -39.3 |  | Link Appveyor | 2 | 4 | -2
Yessica | 128.7 | 133.15 | -4.45 |  | Rect ipoint fpoint | 5 | 4 | 1
Aitor | 42.5 | 49.5 | -7 |  | Link Appveyor | 2 | 4 | -2
Gerard | 12.4 | 73.92 | -61.52 |  | Rect ipoint fpoint | 5 | 4 | 1
Victor | 94.5 | 125.75 | -31.25 |  | Camera | 2 | 3 | -1
[5 empty] | Adding Brofiler | 0.5 | 0.5 | 0
[5 empty] | Doing and testing builds | 1 | 3 | -2
[5 empty] | Review M_SceneManager | 1 | 1 | 0
| You can consult the original excel used during the project by clicking on the following link: |  |  |  | Fix Camera | 2 | 5 | -3
| https://docs.google.com/spreadsheets/d/113tm7NAg_KK83d1rDMhxiy8_wCKlocxPwiix-iR6Y-M/edit?usp=sharing |  |  |  | Test Brofiler | 2 | 1 | 1
[5 empty] | Add Player health | 4 | 2 | 2
[5 empty] | Fix Brofiler | 1 | 1 | 0
[5 empty] | Player stops when he dies | 2 | 1 | 1
[5 empty] | Another player can revive him | 1 | 1 | 0
[5 empty] | Create circle around the player | 1 | 1 | 0
[5 empty] | Improvig the code | 3 | 5 | -2
[5 empty] | Testing builds | 1 | 1 | 0
[5 empty] | Reporting bugs | 1 | 1 | 0
|  |  |  | Aurelio | Logo | 2 | 1.6 | 0.4
[5 empty] | Presentation card | 1 | 1 | 0
[5 empty] | MockUps HUD / Main Menu | 2 | 2.5 | -0.5
[5 empty] | UI Doc > Menu Specification | 4 | 3.8 | 0.2
[5 empty] | UI Doc > In-Game Specifications | 4 | 3 | 1
[5 empty] | UI Doc > Atlas | 5 | 6 | -1
[5 empty] | UI Doc > General | 2 | 2.5 | -0.5
[5 empty] | Module UI > Add Module UI | 2 | 3 | -1
[5 empty] | Module UI > Add STL Containers | 3 | 3.5 | -0.5
[5 empty] | Module Collision > Add STL | 1 | 1 | 0
[5 empty] | Module Collision > Improve | 7 | 12.5 | -5.5
[5 empty] | Module Collision > Debug | 2 | 2 | 0
[5 empty] | Module Map > DrawIsometricQuad | 1 | 1.2 | -0.2
[5 empty] | Module Collision > Research Isometric Collision | 4 | 5 | -1
[5 empty] | Polish Build 0.2 | 2 | 2 | 0
[5 empty] | Module Collision > Add OnTrigge Enter & Exit | 2 | 1 | 1
[5 empty] | Module UI > Improvement Pivot | 2 | 0.5 | 1.5
[5 empty] | Collision > Add Offset to Collision | 0.5 | 0.5 | 0
[5 empty] | Collision > Callback in Objects | 0.5 | 0.5 | 0
[5 empty] | Module Collision > Bugs Fixing | 3 | 3.5 | -0.5
[5 empty] | Module Collision > Add OnTrigge Enter & Exit | 5 | 8.5 | -3.5
[5 empty] | UI > Create HUD Concept | 3 | 4 | -1
[5 empty] | Module UI > Add bars | 2 | 2.2 | -0.2
[5 empty] | GUI > Arrows pointing players | 3 | 4.5 | -1.5
[5 empty] | GUI > Add item/weapon indicator | 3 | 1.5 | 1.5
[5 empty] | HUD > Add HUD Class | 4 | 3.5 | 0.5
[5 empty] | UI > Update Atlas | 2 | 2.5 | -0.5
[5 empty] | Colllision > Solve Bug Collision List | 2 | 1.5 | 0.5
[5 empty] | Module UI > Implement Pivots | 2 | 3 | -1
[5 empty] | UI > Add Main Menu | 3 | 3 | 0
[5 empty] | UI > Update Atlas ( icons, frames ) | 2.5 | 2.5 | 0
[5 empty] | GUI > Implement charged shot Feedback | 2.5 | 2.5 | 0
[5 empty] | GUI > Add icons | 1.5 | 1 | 0.5
[5 empty] | GUI > Add items in game element | 1.5 | 1.5 | 0
[5 empty] | GUI > Add weapons in game element | 2.5 | 4 | -1.5
[5 empty] | GUI > Connect all to players and rounds | 5 | 8 | -3
[5 empty] | Module UI > Add Split Screen In Game Elements | 3 | 5.5 | -2.5
[5 empty] | GUI > Add helpers | 2 | 6.5 | -4.5
[5 empty] | GUI > Pass Round Feedback | 2 | 2 | 0
[5 empty] | GUI > Single camera and not in camera UI Draw Types | 2 | 2.5 | -0.5
[5 empty] | UI > GameOver | 1 | 1 | 0
[5 empty] | UI > Add FXS | 2 | 2.5 | -0.5
[5 empty] | Map > Fix high ms problem | 3.5 | 4 | -0.5
[5 empty] | Game Reset > Add Reset Methods | 4 | 6.5 | -2.5
[5 empty] | Game Loop > Added game over funcionality | 1 | 1.5 | -0.5
[5 empty] | UI > Add Game Over Screen | 2 | 2 | 0
[5 empty] | Game Reset > Organize modules need for reset | 3 | 3 | 0
[5 empty] | UI > Adjust screen resolution | 1 | 1 | 0
[5 empty] | App > Config var to skip main menu | 0.75 | 0.75 | 0
[5 empty] | Collision > Fix Laser | 2 | 5 | -3
[5 empty] | Collision > Fix Missile | 2 | 4 | -2
[5 empty] | UI > Fix Main Menu Navigation | 2 | 3 | -1
[5 empty] | UI > LeaderBoard | 8 | 8 | 0
[5 empty] | UI > Selection Screen | 8 | 10 | -2
[5 empty] | Collision Bugs | 2 | 6 | -4
|  |  |  | Gerard | Introduction | 0.1 | 0.1 | 0
[5 empty] | Code style | 5.75 | 7.25 | -1.5
[5 empty] | Version list | 0.2 | 0.15 | 0.05
[5 empty] | Build delivery method | 0.5 | 0.5 | 0
[5 empty] | Wiki corrections | 1 | 2 | -1
[5 empty] | Build delivery method | 0.5 | 0.25 | 0.25
[5 empty] | QA Introduction | 0.1 | 0.07 | 0.03
[5 empty] | QA Bug properties | 1.5 | 2.25 | -0.75
[5 empty] | QA Process for QC | 1.25 | 1.25 | 0
[5 empty] | Prototype collaboration | 1.5 | 1.25 | 0.25
[5 empty] | TDD corrections | 1.5 | 2 | -0.5
[5 empty] | Base code | 0.3 | 0.6 | -0.3
[5 empty] | Pathfinding module | 0.5 | 2.75 | -2.25
[5 empty] | Adapt project code according to TDD | 1.5 | 2.5 | -1
[5 empty] | Accept pull requests | 2 | 2 | 0
[5 empty] | Enemies pathfind, walkability | 8 | 4 | 4
[5 empty] | Enemies attack | 6 | 2 | 4
[5 empty] | Wave system | 8 | 7.5 | 0.5
[5 empty] | Reward Zones | 10 | 6.75 | 3.25
[5 empty] | Tesla attack animation | 1.5 | 2 | -0.5
[5 empty] | Read reward zones from tiled (had to remember how to do it) | 3 | 3.5 | -0.5
[5 empty] | Win condition | 1.5 | 2.5 | -1
[5 empty] | Fix move tutorial bug | 0.2 | 0.5 | -0.3
[5 empty] | Fix tank shoot down bug | 1 | 1 | 0
[5 empty] | Brute idle state | 0.5 | 1.5 | -1
[5 empty] | Tesla idle state | 0.5 | 1.5 | -1
[5 empty] | Suicidal enemy | 2 | 2.5 | -0.5
[5 empty] | RocketLauncher enemy | 3 | 1.5 | 1.5
[5 empty] | Suicidal enemy | 2 | 4 | -2
[5 empty] | RocketLauncher enemy | 3 | 8 | -5
[5 empty] | Fix bug: tank can pickup item when is dead | 0.3 | 1 | -0.7
[5 empty] | Tank move slower when charging shot | 0.5 | 1 | -0.5
[5 empty] | General adjustments | 1 | 1.5 | -0.5
|  |  |  | Jaume | Wiki supervision | 4 | 6 | -2
[5 empty] | General Analysis | 2 | 2 | 0
[5 empty] | Sprite extraction | 8 | 12 | -4
[5 empty] | GDD > Tutorial | 1 | 1.5 | -0.5
[5 empty] | Welcome page | 2 | 1.5 | 0.5
[5 empty] | Prototype | 6 | 6 | 0
[5 empty] | Player movement | 5 | 0 | 5
[5 empty] | Rotated sprites | 0 | 2 | -2
[5 empty] | App veyor | 0 | 1.5 | -1.5
[5 empty] | First enemy | 0 | 3.45 | -3.45
[5 empty] | Change module names | 2 | 2 | 0
[5 empty] | Player shooting | 3 | 3 | 0
[5 empty] | Weapons structure | 1.5 | 1.5 | 0
[5 empty] | input priorization | 4 | 4 | 0
[5 empty] | Player movement | 3 | 3 | 0
[5 empty] | player weapons | 1.5 | 0 | 1.5
[5 empty] | bullet | 1.5 | 1 | 0.5
[5 empty] | rect class | 2 | 2 | 0
[5 empty] | correct movement | 2 | 2 | 0
[5 empty] | paint enemy again | 2 | 1.5 | 0.5
[5 empty] | sprite sorting | 2 | 7.5 | -5.5
[5 empty] | renames | 1 | 4 | -3
[5 empty] | enenmy revision | 0 | 0.45 | -0.45
[5 empty] | splitscreen | 2 | 3.5 | -1.5
[5 empty] | animation rework | 2 | 1.5 | 0.5
[5 empty] | bullet damage | 0.5 | 1 | -0.5
[5 empty] | Item class | 3 | 3 | 0
[5 empty] | Each player has its own weapons | 2 | 3 | -1
[5 empty] | animation rework merge | 0.5 | 1 | -0.5
[5 empty] | ui (collab programming) | 1 | 1 | 0
[5 empty] | design weapons (collab programming) | 1 | 1 | 0
[5 empty] | special shoot support | 0.5 | 0.5 | 0
[5 empty] | health bag | 1.5 | 3 | -1.5
[5 empty] | build revision | 0.25 | 1 | -0.75
[5 empty] | animation bank | 2 | 2.75 | -0.75
[5 empty] | item: instant help | 1.5 | 0 | 1.5
[5 empty] | move the tank with different keys | 0.5 | 0.5 | 0
[5 empty] | readapt controls | 4 | 2.5 | 1.5
[5 empty] | particle system | 5 | 0 | 5
[5 empty] | tutorial | 3 | 0 | 3
[5 empty] | help with reviving | 5 | 3.75 | 1.25
[5 empty] | wepons structure | 2 | 0 | 2
[5 empty] | tank aiming slightly off | 0.5 | 0.5 | 0
[5 empty] | aim bug + map + weapons structure + tutorial | 18.25 | 18.25 | 0
[5 empty] | map | 5.5 | 5.5 | 0
[5 empty] | bug objects not drawn | 1.5 | 1.5 | 0
[5 empty] | player revive | 7.75 | 7.75 | 0
[5 empty] | draw circle |  |  | 0
[5 empty] | enemy white sprites, camera follows where you're aiming, enemy size | 4 | 4 | 0
[5 empty] | revive circle isometric | 1 | 2 | -1
[5 empty] | bugfixing (collab programing just before release) | 3 | 7 | -4
[5 empty] | sustained shot support | 2 | 1.75 | 0.25
[5 empty] | production plan | 2 | 2 | 0
[5 empty] | design items | 2 | 2 | 0
[5 empty] | collab programming | 3 | 3 | 0
[5 empty] | particle system | 4 | 6 | -2
[5 empty] | bug: if brute comes from bellow the tank, it mantains moving and doesn't attack ever the tank | 1 | 1 | 0
[5 empty] | run over enemies | 3 | 3 | 0
[5 empty] | enemy weapon progression defined in a spreadsheet | 2 | 2 | 0
[5 empty] | map design | 4 | 4 | 0
[5 empty] | particle system | 3 | 3 | 0
[5 empty] | add enemies, weapons and items to gdd | 1.5 | 1.5 | 0
[5 empty] | bug: if brute comes from bellow the tank, it mantains moving and doesn't attack ever the tank | 2 | 0 | 2
[5 empty] | run over enemies | 3 | 0 | 3
[5 empty] | enemy weapon progression defined in a spreadsheet | 2 | 3 | -1
[5 empty] | particle system | 3 | 0 | 3
[5 empty] | healing shot charged | 1 | 0 | 1
[5 empty] | install xcc gerard | 1 | 1.5 | -0.5
[5 empty] | install xcc jorge | 1 | 1.5 | -0.5
[5 empty] | collaborative programming | 4 | 5 | -1
[5 empty] | load objects without colliders in tiled | 0.5 | 0.5 | 0
[5 empty] | fix double missile | 0.5 | 1 | -0.5
[5 empty] | improve aiming | 3 | 5 | -2
[5 empty] | balance from file + issues organization | 5 | 5.75 | -0.75
[5 empty] | issues | 0.5 | 1 | -0.5
[5 empty] | organization + flamethrower + healing shot sprite + change vibration |  | 6 | -6
|  |  |  | Jorge | Production Plan: Sprints | 2 | 2 | 0
[5 empty] | Creation Excel Registry | 1 | 1.5 | -0.5
[5 empty] | Production Plan: Milestones | 0.5 | 0.5 | 0
[5 empty] | Production Plan: Calendar | 3 | 3 | 0
[5 empty] | Production Plan: How are we going to organize | 1 | 2 | -1
[5 empty] | Production Plan: Meetings and Postmortems | 1 | 1 | 0
[5 empty] | Production Plan: Gantt chart | 1 | 2 | -1
[5 empty] | Production Plan: Risk and Contingency | 2 | 3 | -1
[5 empty] | Production Plan: Polish | 2 | 4.5 | -2.5
[5 empty] | Analisys of the original game: Franchise | 0.5 | 1.5 | -1
[5 empty] | Art bible: Art style | 2 | 1 | 1
[5 empty] | Analisys of the original game: History of the game | 1 | 1.5 | -0.5
[5 empty] | Excel: Clasify the registry tasks by sprints | 0.5 | 0.2 | 0.3
[5 empty] | Excel: Add drop-down in excel | 0.5 | 0.5 | 0
[5 empty] | Excel: Consider and record wich researchs can be useful to us | 0.5 | 1 | -0.5
[5 empty] | Excel: Add examns and important assigments to our calendar | 0.3 | 0.15 | 0.15
[5 empty] | Implement module Fonts | 0.2 | 1 | -0.8
[5 empty] | Shoot of the player: Creation of a bullet | 1 | 0.5 | 0.5
[5 empty] | Shoot of the player: Draw the bullet as a rectangle until there is a sprite | 1 | 0.5 | 0.5
[5 empty] | Shoot of the player: Take the variables from the XML | 0.1 | 0.1 | 0
[5 empty] | Shoot of the player: Calculate direction of the bullet with mouse | 2 | 3 | -1
[5 empty] | Shoot of the player: add parent class for weapons inherited from object | 1 | 5 | -4
[5 empty] | Shoot of the player: Shoot continously while the button is held | 0.5 | 0.5 | 0
[5 empty] | Shoot of the player: Updating with the pull request | 0.5 | 2 | -1.5
[5 empty] | Shoot of the player: Polish | 0 | 1.25 | -1.25
[5 empty] | Excel: formulario to excel | 1 | 2.25 | -1.25
[5 empty] | Splitscreen: investigation | 4 | 2 | 2
[5 empty] | Splitscreen: 4 cameras sitauted correctly | 0.5 | 0.5 | 0
[5 empty] | Splitscreen: camera limits | 1 | 2.5 | -1.5
[5 empty] | Splitscreen: camera with the correct size | 0.1 | 0.1 | 0
[5 empty] | Splitscreen: class camera | 0.5 | 0.5 | 0
[5 empty] | Splitscreen: add 4 cameras in total | 0.5 | 3.25 | -2.75
[5 empty] | Splitscreen: Fix problem with camera limits left and up | 1 | 0.1 | 0.9
[5 empty] | Splitscreen: Optimization | 1.5 | 5 | -3.5
[5 empty] | Splitscreen: margins v1 | 1 | 0.25 | 0.75
[5 empty] | Splitscreen: debug v1 | 1 | 0.1 | 0.9
[5 empty] | Decide in group the code structure of the items | 1 | 1 | 0
[5 empty] | Managment | 5 | 3 | 2
[5 empty] | PickupManager | 2 | 3 | -1
[5 empty] | Splitscreen: debug v2 | 0.5 | 0.5 | 0
[5 empty] | Splitscreen: Merge | 0.5 | 3 | -2.5
[5 empty] | Splitscreen: Optimization v2 | 5 | 2.5 | 2.5
[5 empty] | Splitscreen: polish code | 1 | 2.5 | -1.5
[5 empty] | Splitscreen: The drawLine has to respect the splitscreen | 1 | 2 | -1
[5 empty] | Take items from the floor | 2 | 3.25 | -1.25
[5 empty] | Test Build | 0 | 0.25 | -0.25
[5 empty] | Fixing DrawCircle | 0.25 | 0.5 | -0.25
[5 empty] | Managment | 2 | 7.5 | -5.5
[5 empty] | Read Spawners box from tiled | 2 | 2 | 0
[5 empty] | Create Spawner Boxs from the spawners | 1 | 1 | 0
[5 empty] | Spawner Boxs | 3 | 4 | -1
[5 empty] | Polish | 2 | 0.5 | 1.5
[5 empty] | PickUps level in weapons | 1 | 2 | -1
[5 empty] | Read Spawners enemy and Reward Zones from tiled | 1 | 1.5 | -0.5
[5 empty] | Check the spawn wave | 3 | 4.5 | -1.5
[5 empty] | Merge | 0.15 | 1.5 | -1.35
[5 empty] | Fixing bar lyfes and other bugs | 0.5 | 3 | -2.5
[5 empty] | get buildings from tiled | 1 | 4.5 | -3.5
[5 empty] | Box sprite | 0.5 | 1.5 | -1
[5 empty] | PickUp tutorial | 0.5 | 0.25 | 0.25
[5 empty] | Recoil | 1 | 1.5 | -0.5
[5 empty] | death animation tesla trooper | 1 | 1.5 | -0.5
[5 empty] | Actualizar retroceso | 1 | 0.5 | 0.5
[5 empty] | read pivots from buildings from tiled | 0.5 | 0.25 | 0.25
[5 empty] | bug don't take the pickUp with the controller | 0.5 | 1 | -0.5
[5 empty] | Heal shot don't heal yourself | 1 | 1 | 0
[5 empty] | Laser shot | 1 | 1.45 | -0.45
[5 empty] | brute spawn a weapon | 0.5 | 0.25 | 0.25
[5 empty] | colliders water or wall read from tiled and implemented | 0.5 | 0.5 | 0
[5 empty] | sfx brute and tesla trooper hit and death | 1 | 1 | 0
[5 empty] | Láser charged | 1 | 1 | 0
[5 empty] | Double missile fix (try) | 1 | 1 | 0
[5 empty] | Managment | 2 | 1.25 | 0.75
[5 empty] | Rework to items | 0.5 | 0.5 | 0
[5 empty] | you start the game with an item (botiquin) | 0.5 | 0.1 | 0.4
[5 empty] | item happy hour rework v1 | 2 | 1 | 1
[5 empty] | generic enemy class (with all the methods that are used by most enemies) v1 | 3 | 2.5 | 0.5
[5 empty] | Crashes when you press a lot of buttons at the same time with the controller | 1 | 0 | 1
[5 empty] | Item: Health area | 3 | 1.5 | 1.5
[5 empty] | Item: Bomb | 3 |  | 3
[5 empty] | item happy hour rework v2 (icon) | 0.25 | 0.5 | -0.25
[5 empty] | generic enemy class (with all the methods that are used by most enemies) v2 | 1 | 2 | -1
[5 empty] | modify the way we get a sfx (said he had some improvements) | 1 | 1 | 0
[5 empty] | Managment | 3 | 2.5 | 0.5
[5 empty] | Weapon: Electro shot | 5 | 12 | -7
[5 empty] | Feedback cuando cargas el disparo | 2 | 4.25 | -2.25
[5 empty] | rework basic weapon | 1.5 | 2 | -0.5
[5 empty] | searching sprites | 0 | 1 | -1
[5 empty] | fixing boxes with 4 initial boxes | 0.5 | 0.5 | 0
[5 empty] | fixing bugs | 0 | 3.5 | -3.5
[5 empty] | electroShot don't hit sometimes | 1 | 1 | 0
[5 empty] | Change Textures bug fix | 1 | 0.5 | 0.5
[5 empty] | Managment | 2 | 2 | 0
|  |  |  | Sergio | Narrative | 2 | 4 | -2
[5 empty] | References | 1 | 1 | 0
[5 empty] | Characters | 1 | 2 | -1
[5 empty] | Fonts | 1 | 1.5 | -0.5
[5 empty] | Plot and narrative | 3 | 5 | -2
[5 empty] | Scenarios | 1 | 1 | 0
[5 empty] | Rotate sprite function | 2 | 3 | -1
[5 empty] | Sprite sorting v1 | 3 | 3 | 0
[5 empty] | Sprite sorting v2 | 5 | 7 | -2
[5 empty] | Sprite sorting v3 | 2 | 5 | -3
[5 empty] | Sprite sorting v4 | 2 | 12 | -10
[5 empty] | Rename and organize audios v1 | 0.5 | 0.5 | 0
[5 empty] | Add sound to bullet | 1 | 1.5 | -0.5
[5 empty] | First version of playable map v1 | 8 | 9.5 | -1.5
[5 empty] | First version of playable map v2 | 4 | 22 | -18
[5 empty] | Map corrrection | 2 | 1 | 1
[5 empty] | Enemy: shield v1 | 7 | 9 | -2
[5 empty] | Organize texture folder | 1 | 0.5 | 0.5
[5 empty] | Paint new map | 12 | 17.5 | -5.5
|  |  |  | Víctor | Game pillars | 1 | 3 | -2
[5 empty] | Game Flow | 2 | 2 | 0
[5 empty] | Maps | 1 | 1 | 0
[5 empty] | Target | 0.5 | 0.5 | 0
[5 empty] | Pitch | 3 | 4 | -1
[5 empty] | Weapons | 1 | 2 | -1
[5 empty] | Objects | 1 | 2 | -1
[5 empty] | Stats | 1 | 1 | 0
[5 empty] | Gameplay | 3 | 8 | -5
[5 empty] | Controls | 1 | 0.5 | 0.5
[5 empty] | Enemies | 1 | 1 | 0
[5 empty] | Entity Manager Addition and conversion to STL | 3 | 2 | 1
[5 empty] | Add basic Enemy | 2 | 6 | -4
[5 empty] | Add Background Music | 0.5 | 0.5 | 0
[5 empty] | Map Created | 3 | 3 | 0
[5 empty] | Redesign to encourage Coop Apect | 2 | 2 | 0
[5 empty] | Make bullet collide and make damage to enemy | 2 | 3 | -1
[5 empty] | Double Missiles | 3 | 6 | -3
[5 empty] | Important Redesign (how weapons work and reward zones) | 2 | 1.25 | 0.75
[5 empty] | Redesign Game (GDD) | 1 | 0.75 | 0.25
[5 empty] | Brute | 3 | 7.5 | -4.5
[5 empty] | Happy Hour | 1 | 2.5 | -1.5
[5 empty] | Healing Shot | 3 | 3 | 0
[5 empty] | Balance Game | 5 | 2 | 3
[5 empty] | Add Explosion Fx | 0.5 | 0.5 | 0
[5 empty] | Add Attack Animation tesla trooper | 1 | 2 | -1
[5 empty] | Add Fire Particle when tank dead | 1 | 1.5 | -0.5
[5 empty] | Dead Players Work Correctly | 1 | 1 | 0
[5 empty] | Brute Idle Animation | 0.5 | 0.5 | 0
[5 empty] | Pitch (Power Point) | 1 | 0.75 | 0.25
[5 empty] | Brute Sounds | 0.5 | 0.5 | 0
[5 empty] | Pitch | 1 | 3 | -2
[5 empty] | Design and decide weapons for final version | 2 | 3 | -1
[5 empty] | Design and decide enemies for final version | 2 | 2.5 | -0.5
[5 empty] | Put GDD in order | 0.5 | 0.5 | 0
[5 empty] | Weapon Oil creation | 2 | 2.75 | -0.75
[5 empty] | Weapon Oil Interact with enemies | 3 | 5 | -2
[5 empty] | Double Missile Charged Shot | 0.5 | 0.25 | 0.25
[5 empty] | Fixes | 1 | 2 | -1
[5 empty] | Healing Shot Charged | 2 | 2 | 0
[5 empty] | Presentation Slides | 2 | 2 | 0
[5 empty] | Presentation | 2 | 2 | 0
[5 empty] | Item Barrier | 2 | 1 | 1
[5 empty] | Instant Help Item | 3 | 4 | -1
[5 empty] | Video Player + Logo Video In Game | 3 | 3.5 | -0.5
[5 empty] | Fix Instant Help | 3 | 1.5 | 1.5
[5 empty] | Options Menu | 8 | 10.25 | -2.25
[5 empty] | Pause Menu Creation | 1 | 1 | 0
[5 empty] | Credits Menu | 2 | 5.5 | -3.5
|  |  |  | Yessica | UML | 5 | 4 | 1
[5 empty] | Target Hardware | 3 | 3 | 0
[5 empty] | Performance budgets | 0.2 | 0.2 | 0
[5 empty] | External libraries | 1 | 1 | 0
[5 empty] | Market positioning | 3 | 3 | 0
[5 empty] | technical profile | 1 | 1 | 0
[5 empty] | Genre | 3 | 3 | 0
[5 empty] | Sprites tank 3d | 3 | 3 | 0
[5 empty] | Module Map | 2 | 2 | 0
[5 empty] | Gamepad Controller | 4 | 8 | -4
[5 empty] | Load collisions in tiled | 3 | 0 | 3
[5 empty] | Sprite bullets | 1 | 1 | 0
[5 empty] | Move enemy | 15 | 15 | 0
[5 empty] | Review base code following the TDD guidelines | 1 | 0.75 | 0.25
[5 empty] | Solve controller bug | 1 | 0.5 | 0.5
[5 empty] | quadtree with map drawing | 7 | 10 | -3
[5 empty] | Load colliders in tiled with objects | 5 | 5 | 0
[5 empty] | Review scene manager | 1 | 3 | -2
[5 empty] | Helping with splitscreen | 1 | 1 | 0
[5 empty] | Bug: enemies movement | 4 | 3 | 1
[5 empty] | crashes when adding and removing controllers | 3 | 0.2 | 2.8
[5 empty] | module scene manager | 5 | 4 | 1
[5 empty] | tank aiming slightly off | 2 | 5 | -3
[5 empty] | help with map | 5 | 7 | -2
[5 empty] | add controller vibrations | 0.5 | 0.5 | 0
[5 empty] | add spawn animation | 1 | 1 | 0
[5 empty] | add teleport | 3 | 4 | -1
[5 empty] | sfx tesla trooper attack | 1 | 1 | 0
[5 empty] | bug sfx volum | 1 | 1 | 0
[5 empty] | tank color | 1 | 1 | 0
[5 empty] | circle animation when reviving | 1 | 1 | 0
[5 empty] | fix pathfinding | 1 | 1 | 0
[5 empty] | add god mode | 1 | 1 | 0
[5 empty] | bug: show cursor | 0.5 | 0.5 | 0
[5 empty] | fix teleport | 2 | 5 | -3
[5 empty] | optimize pathfinding | 3 | 3 | 0
[5 empty] | delete margin from qt | 0.5 | 0.5 | 0
[5 empty] | Enemies "pool" | 2 | 2 | 0
[5 empty] | Enemies surround you (more interesting pathfinding) | 5 | 5 | 0
[5 empty] | burnung enemies tha run | 2 | 2 | 0
[5 empty] | brute pathfinding | 3 | 3 | 0
[5 empty] | tesla trooper goes idle | 1 | 4 | -3
[5 empty] | burnung enemies tha run | 2 | 5 | -3
[5 empty] | enemies with two collider | 3 | 3 | 0
[5 empty] | optimize pathfinding | 3 | 6 | -3
[5 empty] | boxes damaged | 1 | 1 | 0
[5 empty] | Multiple waves of enemies | 2 | 3 | -1
[5 empty] | Tesla Trooper goes idle | 1 | 2 | -1
[5 empty] | teleport bug | 1 | 1 | 0
[5 empty] | Fix bridge don't print correct | 1 | 1 | 0
[5 empty] | when you touch an enemy with the flamethrower, it shoud be set on fire | 1 | 2 | -1
[5 empty] | brute y otros bosses deberian hacer teleport como los tesla trooper | 1 | 3 | -2
[5 empty] | Tank flashes white when recieve damage | 2 | 3 | -1